## Slide 1: FRANCHISE INFORMATION PACKETS BY DISCIPLINE DIGITAL

## Slide 2: 特许经营 业务领域信息包 数字化 DIGITAL

## Slide 3
Milestones| BMSC – DIGITAL
MILESTONES | WHO IS RESPONSIBLE
Digital Orientation | Sales, Marketing, Revenue Management and E-commerce
Launch Hotel Web Site | Marketing (DOSM/DOM)
Feature Hotel Photos Online | Marketing (DOSM/DOM)
Activate eTools | Sales (DOSM)
Activate OTAs | Revenue Management
Develop the eMarketing Plan – as part of the Integrated Marketing Plan (including M.com HWS + OTA + Travel Review site activation, PR, social, paid & digital, ad campaign) | DOSM/DOM
Digital Guest Experience | DOSM/DOM
Participate in Vacations by Marriott | Revenue Management
Verify Hotel Listing on 3rd Party Sites | Marketing (DOSM/DOM)
Generate GDS Awareness | Marketing (DOSM/DOM)
Marriott has created a holistic critical path document to complement information packets for all franchised hotels across Asia Pacific. These activities have been organized by department/division, as shown below.

## Slide 4
里程碑 | 品牌、市场、销售和顾客服务 (BMSC) – 数字化 (Digital)
里程碑 | 负责部门
数字化培训 | 销售部、市场部、收益管理部和电子商务部
启动酒店网站（HWS） | 市场部（销售和市场总监/市场总监）
上传酒店照片 | 市场部（销售和市场总监/市场总监）
激活电子工具 | 销售部（销售和市场总监）
激活旅游网站（OTA） | 收益管理部
开发“电子营销计划”—作为“整体营销计划”的一部分（包括激活M.com酒店网站（HWS）+ OTA + 旅游评论网站、公关、社交、支付&数字化、广告宣传） | 销售和市场总监/市场总监
数字化住客体验 | 销售和市场总监/市场总监
参与 Vacations by Marriott（万豪度假服务网站） | 收益管理部
确认第三方网站酒店信息页面 | 市场部（销售和市场总监/市场总监）
培养对于“全球分销系统”（GDS）的认知（员工的意识吗？） | 市场部（销售和市场总监/市场总监）
万豪创建了一份关键路径全面文件，以补充亚太地区所有特许经营酒店的信息数据包。各项工作由以下部门负责统筹，如下表所示。

## Slide 5
Training & Costs | BMSC – DIGITAL
Training | AUDIENCE | MANDATORY/ OPTIONAL | DURATION | TIMING | COST BREAKDOWN (USD)
EPIC Training Energizers: EPIC General Information EPIC How to Use | DOSM, DOM, Marcom Team | Optional | 30 min. each | Recommended: 6 months before opening | https://extranet.marriott.com/mgs/common/sales-mktg-and-rev-mgmt/ecommerce/epic https://extranet.marriott.com/mgs/common/sales-mktg-and-rev-mgmt/ecommerce/epic/checklist.html
Pre-Opening Digital Orientation | DORM, DOSM, DOM, Marcom Team, eCommerce Manager | Optional | 1 day | Recommended: 4 months before opening | Digital Services Leader’s flight, ground transfers & hotel accommodation only
Self-Paced Training – Review eCommerce Section of Marriott Global Source (MGS) | DORM, DOSM, DOM, Marcom Team | Optional | 2 days | Recommended: 3 months before opening | https://extranet.marriott.com/mgs/common/sales-mktg-and-rev-mgmt/ecommerce
eTools Training Energizers: Custom Webpage eGroup List eRooming List eTools ResLink Direct | DOSM, Sales Team | Optional | 30 min. each | Recommended: 2 months before opening | https://extranet.marriott.com/mgs/common/business-resources/business-applications/etools/default.html https://extranet.marriott.com/mgs/common/sales-mktg-and-rev-mgmt/ecommerce/marketing-to-groups-and-corporations/etools-help.html
Marriott Global University | DOSM, DOM, Sales, Revenue, Marketing, eCommerce | Optional | 1 day | On-going; Please refer to email from Director of BMSC Training & Global Learning Network | Approx. $300 per attendee + cost of travel (if needed, based on the location of the class)
eCommerce Global Conference Calls | DOSM, DOM, Marcom Manager, eCommerce Manager | Optional | 1 hour | Monthly | Dan.Melluzzo@marriott.com for application

## Slide 6
培训和成本 | 品牌、市场、销售和顾客服务 (BMSC) – 数字化 (Digital)
培训内容 | 对象 | 强制/自选 | 时长 | 时间安排 | 成本明细（美元）
企业资产信息中心 (EPIC) 培训要点： • EPIC基本信息 • EPIC使用入门 | 销售和市场总监、销售总监、公关部 | 自选 | 每项30分钟 | 建议：距开业6个月 | https://extranet.marriott.com/mgs/common/sales-mktg-and-rev-mgmt/ecommerce/epic https://extranet.marriott.com/mgs/common/sales-mktg-and-rev-mgmt/ecommerce/epic/checklist.html
开业前数字化培训 | 收益管理总监、销售和市场总监、销售总监、公关部、电子商务经理 | 自选 | 1天 | 建议：距开业4个月 | 仅包括数字化服务负责人的机票、车辆及酒店住宿费
自学培训—复习万豪全球资源 (MGS)中的电子商务部分 | 收益管理总监、市场销售总监、销售总监、公关部 | 自选 | 2天 | 建议：距开业3个月 | https://extranet.marriott.com/mgs/common/sales-mktg-and-rev-mgmt/ecommerce
网络工具培训要点： • 网页定制 • 电子群组列表 • 电子订房列表 • 电子工具 • 直接预订链接 (ResLink Direct) | 销售和市场总监、销售部 | 自选 | 每项30分钟 | 建议：距开业2个月 | https://extranet.marriott.com/mgs/common/business-resources/business-applications/etools/default.html https://extranet.marriott.com/mgs/common/sales-mktg-and-rev-mgmt/ecommerce/marketing-to-groups-and-corporations/etools-help.html
万豪全球大学 Marriott Global University | 销售和市场总监、销售总监、收益管理部、市场营销部、电子商务部 | 自选 | 1天 | 持续进行，请参考 “BMSC培训&全球学习网络”项目负责人的邮件 | 约300美元/位培训员工+旅行费用（如有该项费用，则依授课地点而定）
电子商务全球电话会议 | 销售和市场总监、销售总监、公关经理、电子商务经理 | 自选 | 1小时 | 每月例行 | Dan.Melluzzo@marriott.com 申请会议参加资格，获得审批后，邮件接收会议通知和内容

## Slide 7
Additional Services & Costs | BMSC – DIGITAL
SERVICE | DESCRIPTION | MANDATORY / OPTIONAL | TIMING | COST (USD)
Hotel Web Site Copywriting | Copywriting for all or some of the free-form copy blocks on your Marriott.com Hotel Web Site, depending on hotel type and brand. | Optional | 3 months before opening | Select Service: $505 Full Service: $760
Hotel Web Site Vanity URL | Get a short and memorable URL for your Hotel Web Site that you can use in your marketing collateral. | Optional | 6 months before opening | $246 per URL (for the first 2 years)
Hotel Web Site Product Marketing Modules | Product Marketing Modules enable you to extend your hotel website, by providing additional pages of content to promote your hotel’s features and unique selling points – e.g. meetings, weddings, spas, golf, restaurants, etc. | Optional | 3 months before opening | Set up cost of $350 per page (with a complimentary Photo Tour) based on a module of 1-10 pages. Includes maintenance fee in year 1
Digital Shared Service | Participate in the Digital Shared Service to tap into the expertise of our in-market digital services team, who can provide comprehensive support in the lead up to your hotel opening as well as ongoing support and guidance post-opening. | Optional | 3 months before opening | Varies. Please contact your Area Director of Sales & Marketing
PLUS Platform | PLUS is a digital advertising platform that connects hotels to consumer demand everywhere travelers shop. PLUS allows individual hotels to layer funds on top of Marriott Corporate spend, to increase exposure and drive more direct bookings. | Optional | Post Opening | Min. initial deposit of $250
Digital Services: Foundations Program | This core Search Engine Optimization service (with optional add-on bundles) helps increase your hotel’s visibility in search engines, so as to drive more traffic and room nights | Optional | Post Opening | $5,500 per year Optional add-on bundles at $1,300 - $4,000 each per year
Digital Services: Signature+ Program | This comprehensive Digital Activation program includes development and execution of a detailed Digital Business Plan that is customized for your hotel, with the goal of increasing online room nights and revenue for your hotel. | Optional | Post Opening | $25,000

## Slide 8
其他服务和成本 | 品牌、市场、销售和顾客服务 (BMSC) – 数字化 (Digital)
服务项目 | 服务内容 | 强制/自选 | 时间安排 | 成本（美元）
酒店网站文案 | 在Marriott.com酒店网站(HWS)上，根据酒店的类型和品牌在全部或部分自由板块上设计文案。 | 可选 | 距开业3个月 | 部分服务：505美元 全套服务：760美元
酒店网站名义网址 (URL) | 为酒店网站创建一个简短好记的网址，可用于营销宣传资料。 | 可选 | 距开业6个月 | 246美元/个URL（2年）
酒店网站 产品营销模块 | 产品营销模块可用于扩展酒店网站，额外增加页面内容以推广酒店的特色及特卖点——例如会议场地、婚礼场地、spa服务、高尔夫、餐厅等。 | 可选 | 距开业3个月 | 对于1-10页的模块，创建费用为每页350美元（免费赠送照片展示Photo Tour），包括1年的维护费。
数字共享服务 | 参与到数字共享服务中，充分发挥市场数字化服务团队的专业技能优势，全面支持酒店开业前期的准备，并支持指导后续的进程。 | 可选 | 距开业3个月 | 价格各异。请联系所在地区的区域市场营销总监。
PLUS平台 | PLUS是一个数字广告平台，可在游客所到之处将消费者需求与酒店对接。每家酒店可以在万豪集团广告费用的基础上再增加广告支出，从而可以提高曝光率，增加自身的直接预订量。 | 可选 | 开业后 | 最低初始保证金为250美元
数字化服务: 基础项目 | 核心搜索引擎优化服务（可选带插件包），有助于提高酒店在搜索引擎上的曝光度，进而扩大网站访问量，增加间夜总量。 | 可选 | 开业后 | 每年5500美元 可选插件包每个1300-4000美元/年
数字化服务: 签名+项目 | 全面激活数字化计划，包括开发执行为酒店定制的详细数字化业务计划，以提高酒店的间夜量及收益额。 | 可选 | 开业后 | 25000美元

## Slide 9
Resources & Contacts| BMSC – DIGITAL
RELEVANT MGS LINKS | DESCRIPTION
https://extranet.marriott.com/mgs/common/sales-mktg-and-rev-mgmt/ecommerce | eCommerce section of MGS, which contains a wealth of resources to help hotels optimize results from M.com & OTAs
https://extranet.marriott.com/mgs/common/sales-mktg-and-rev-mgmt/ecommerce/hws-users-guide | Hotel Web Sites (HWS) User Guide with detailed information to help hotels update their content on M.com and our Global sites
https://extranet.marriott.com/mgs/common/sales-mktg-and-rev-mgmt/ecommerce/emarketing | Provides guidance on how to drive more qualified traffic to your HWS, and generate more RNs and bookings
https://extranet.marriott.com/mgs/common/sales-mktg-and-rev-mgmt/ecommerce/online-travel-agencies/1online-travel-agencies-strategy/frequently-asked-questions.html | OTA participation guidelines and documentation for hotels.
http://epic.marriott.com | Link to EPIC, an online database of hotel information that supports multiple systems, including your HWS
https://extranet.marriott.com/etools/ | Link to eTools
https://extranet.marriott.com/MRDWWebApp/mrdw/mrdwHome.do | Link to MRDW, where you can access hotel performance reports

## Slide 10
联系方式和资源链接| 品牌、营销、销售和顾客服务 (BMSC) – 数字化 (Digital)
万豪全球资源（MGS）相关链接 | 网站内容
https://extranet.marriott.com/mgs/common/sales-mktg-and-rev-mgmt/ecommerce | MGS电子商务部分，在介绍如何优化M.com及OTA的搜索结果方面提供了丰富的信息
https://extranet.marriott.com/mgs/common/sales-mktg-and-rev-mgmt/ecommerce/hws-users-guide | 酒店网站 (HWS)用户指南，详细指导说明了如何更新M.com及万豪全球网站上的内容。
https://extranet.marriott.com/mgs/common/sales-mktg-and-rev-mgmt/ecommerce/emarketing | 介绍了如何提高酒店网站（HWS）的访问量，进而增加酒店的间夜量及预订量。
https://extranet.marriott.com/mgs/common/sales-mktg-and-rev-mgmt/ecommerce/online-travel-agencies/1online-travel-agencies-strategy/frequently-asked-questions.html | 酒店与旅游网站（OTA）的合作指南和文档资料。
http://epic.marriott.com | 酒店信息在线数据库EPIC的网址，此数据库支持包括酒店网站（HWS）等多种系统。
https://extranet.marriott.com/etools/ | 网络工具的网址。
https://extranet.marriott.com/MRDWWebApp/mrdw/mrdwHome.do | 万豪房间预订数据库（MRDW）的网址，可查看酒店的业绩报告。